## Summary Activities
Ultimate Outcome | Intermediate Outcomes | Immediate Outcome | Output | Activity |  | 2020 | [11 empty] | Responsible Party | Budget Allocation (USD) | Funding Agency
[6 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1000 Oversight and Active Participation of Multi-Stakeholder Group of Activities and Reports to Promote Transparency and Accountability | 1100 Effective multi-stakeholder oversight, including a functioning multi-stakeholder group that involves the government, companies and the full, independent, active and effective participation of civil society | 1200 Ensure government commitment company and civil society engagement, establishment and functioning multi-stakeholder group, agreed work plan, clear objectives, and realistic timetable, aligned with deadlines established by the EITI Board | 1300 Output – Government Commitment of AEITI Principles and Standards | 1301 | Statement from H.E. Minister MoMP-GoIRA on continued support of AEITI | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 1302 | Publish MoMP & MoF- GoIRA Support Statement on AEITI Website | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Feb
|  |  |  | 1303 | Openning Cermoney (singing charter) Event for the new MSG | [12 empty] | AEITI Sec | 1000 | GIZ | bar: Q1 Mar
|  |  |  | 1304 | Charter with All New MSG Members as Signatories (Post-Election) | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Mar
|  |  |  | 1305 | Sign MoU among Relevant Gov Stakeholders for EITI implementaion | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Feb
|  |  | 1400 Output – Strengthen AEITI administrative and financial operational procedures | 1401 | MSG consultation and approval of documents & operational procedures | [12 empty] | MSG/WG | 700 | GIZ | bar: Q1 Mar to Q2 Apr
|  |  |  | 1402 | Develop distribute MSG Operational Guidebook/Manual | [12 empty] | AEITI Sec | 300 | GIZ | bar: Q2 Apr to Q2 May
|  |  |  | 1403 | Prepare AEITI MSG Gender Policy | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Feb
|  |  |  | 1404 | Review Secretariat ToRs and update to reflect any required changes | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 1405 | Re-structure filing and record keeping systems through digitization | Q1 Jan: To be implemented in 2021
|  |  | 1500 Output – Ensure transparent MSG Election Procedure & Gender Balance | 1501 | Prepare and implement Exit Survey with departing MSG Members | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan to Q1 Feb
|  |  |  | 1502 | Map MSG constituent (entity level) membership base and disclose | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Mar
|  |  |  | 1503 | CSOs and Private Sector to develop transparent election procedures | [12 empty] | CSO & PS | 0 | GIZ | bar: Q1 Jan
|  |  |  | 1504 | Hold Election for industry and civil society and introduce Gov representatives | [12 empty] | CSO & PS | 2000 | GIZ | bar: Q1 Jan to Q1 Feb
|  |  |  | 1505 | Monitoring of election process, recording and disclosure of process | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan to Q1 Feb
|  |  |  | 1506 | Appointment of MSG NEW Chair & Co-chair | [12 empty] | GoIRA | 0 | NA | bar: Q1 Mar
|  |  |  | 1507 | Identification of new Working Group members | [12 empty] | MSG | 0 | NA | bar: Q1 Mar
|  |  |  | 1508 | Creation of a Gender Focused Working Group | [12 empty] | MSG | 0 | NA | bar: Q1 Mar
|  |  |  | 1509 | Review gender barriers (if any) and decide on maximization | Q1 Jan: To be implemented in 2021
|  |  |  | 1510 | Design and implement a qualitative survey | Q1 Jan: To be implemented in 2021
|  |  |  | 1511 | Develop a Gender strategy to maximize female participation in the MSG | Q1 Jan: To be implemented in 2021
|  |  | 1600 Output – Strengthening knowledge base, capacity and skills for AEITI/MSG | 1601 | Induction Training on EITI and Operations Guidebook for Incumbent MSG | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Feb to Q1 Mar
|  |  |  | 1602 | Team Building Retreat with new MSG and Secretariat | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Mar
|  |  |  | 1603 | Workshops to geology & mining related university students | [12 empty] | AEITI Sec | 500 | GIZ | bar: Q2 May
|  |  |  | 1604 | Capacity building 'Study Tour' for MSG & AEITI Secretariat | [12 empty] | MSG | 30000 | GIZ | bar: Q2 Apr; Q3 Sep
|  |  |  | 1605 | Peer learning and capacity development for MSG members and AEITI staffs | [12 empty] | AEITI Sec | 50000 | WB | bar: Q2 May; Q3 Jul; Q3 Sep
|  |  |  | 1606 | Stakeholder Engagement and Communications Training (MSG & Secretariat) | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 May
|  |  |  | 1607 | AEITI MSG and Secretariat participation Mining Oil and Gas Conference (INDABA 2021) | Q1 Jan: To be implemented in 2021
|  |  | 1700 Output – Annual MSG Annual Workplan (including Budget & Procurement Plan) | 1701 | Review of 2020 Workplan, ensure targets are met, revise and report | [12 empty] | MSG | 0 | NA | bar: Q2 Jun; Q4 Oct
|  |  |  | 1702 | MSG Consultation with wider Constituencies for 2021 Workplan | [12 empty] | MSG | 4000 | GIZ | bar: Q3 Sep to Q4 Oct
|  |  |  | 1703 | AEITI Progress Review, Impact Assessment and 2021 Workplan Planning Session | [12 empty] | AEITI Sec | 20000 | GIZ | bar: Q4 Nov
|  |  |  | 1704 | 2021 Workplan Review and Approval by MSG | [12 empty] | MSG | 0 | NA | bar: Q4 Dec
|  |  | 1800 Output – Timely disclosure of Annual AEITI Reports based on EITI requirements. | 1801 | Print and dissemination of the 6th AEITI report | [12 empty] | AEITI Sec | 6000 | WB | bar: Q1 Jan to Q1 Feb
|  |  |  | 1802 | Recruitment and appointment of Independent Administrator for 7th report | [12 empty] | AEITI Sec | 100000 | WB | bar: Q1 Jan to Q1 Mar
|  |  |  | 1803 | Training on Reporting Templates with Identified Directorates and Companies | [12 empty] | IA | 0 | NA | bar: Q1 Mar
|  |  |  | 1804 | Working Groups (G1 & G-3) Coordinate with Independent Administrator for preparation of 7th report and oversee the report development process | [12 empty] | MSG | 0 | NA | bar: Q1 Mar to Q3 Sep
|  |  |  | 1805 | Presentation, approval and publication of the 7th AEITI report | [12 empty] | MSG | 0 | NA | bar: Q4 Oct
|  |  |  | 1806 | Publish 7th AEITI summary report through briefings/news items | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Oct
|  |  |  | 1807 | Print and dissemination of 7th AEITI report | [12 empty] | AEITI & MoMP | 6000 | WB | bar: Q4 Nov to Q4 Dec
|  |  |  | 1808 | Workshop on lesson learned form 7th AEITI report (to relevant stakeholders) | [12 empty] | MSG/WG | 1000 | GIZ | bar: Q4 Nov
|  |  |  | 1809 | Preparation of 2019 Annual Progress Report - all stakeholders | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 1810 | Translation and publication of 2019 Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 1811 | Preparation of Draft 2020 Annual Progress Report - all stakeholders | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Nov
|  |  |  | 1812 | MSG revision and Approval of the 2020 Annual Progress Report | [12 empty] | MSG | 0 | NA | bar: Q4 Nov
|  |  |  | 1813 | Translation and publication of 2020 Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  |  | 1814 | Resolving descripancy of 3-5 AEITI Report | [12 empty] | AEITI Sec | 20000 | WB | bar: Q1 Mar to Q2 Jun
|  |  |  | 1815 | Gender Working Group inclusion of Gender Responsive Review and Strategy | Q1 Jan: To be implemented in 2021
|  |  |  | 1816 | Recruitment of Independent Administrator for 8th AEITI Report (2019 and 2020) | Q1 Jan: To be implemented in 2021
|  |  |  | 1817 | WG-4 gaps analysis, review and reconciliation based on 7th IA and Validation comments | Q1 Jan: To be implemented in 2021
|  |  | 1900 Output – Re-validation of AEITI MSG to left the suspension | 1901 | Update 2019 Action Plan (to 2020) | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 1902 | Preparation of Addendum for the 6th AEITI Report and MSG approval | [12 empty] | MoMP & MSG | 0 | NA | bar: Q1 Jan
|  |  |  | 1903 | Address Validaiton, 5th and 6th AEITI reports' recommendations | [12 empty] | MSG | 0 | NA | bar: Q1 Jan to Q1 Feb
|  |  |  | 1904 | MSG Meeting to determine Re-Validation Timeline and Request | [12 empty] | MSG | 0 | NA | bar: Q1 Feb to Q1 Mar
|  |  |  | 1905 | AEITI Secretariat to share all documents and information with EITI Secretariat | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Apr
2000 Improving and enhancing transparency and accountability in the legal and institutional framework, including allocation of contracts and licenses for public disclosure and advocacy | 2100 Disclosures on how the Extractive Sector is managed, enabling stakeholders to understand the laws and procedures for the award of exploration and production rights, the legal, regulatory and contractual framework that applies to the extractive sector and institutional responsibilities of the State in managing the sector. | 2200 The EITI Requirements related to a transparent legal framework and awarding of extractive industry rights include: (2.1) legal framework and fiscal regime; (2.2) contract and license allocations; (2.3) register of licenses; (2.4) contracts; (2.5) beneficial ownership; and (2.6) state participation in the extractive sector. | 2300 Output – Gaps Analysis, legal, regulatory and policy frameworks | 2301 | Conduct a Gaps Analysis (GA) Report resulting in key recommendations (WG 1-4) | [12 empty] | MSG | 0 | NA | bar: Q3 Jul
|  |  |  | 2302 | Present findings to MSG and other key (identified) stakeholder | [12 empty] | MSG | 0 | NA | bar: Q3 Aug
|  |  |  | 2303 | Implement a Gender Round-table Discussion to gain Gender Responsive Recommendations | [12 empty] | AEITI Sec | 0 | NA | bar: Q3 Sep
|  |  |  | 2304 | Publicly disclose any legal, regulatory and policy changes on MoMP/AEITI Websites | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Mar; Q2 Jun; Q3 Sep; Q4 Dec
|  |  |  | 2305 | Publicly disclose all active contracts and licenses on Transparency Portal | [12 empty] | MoMP | 0 | NA
|  |  |  | 2306 | Systematic disclosure of transparent tendering and bidding procedures and license award | [12 empty] | MoMP | 0 | NA
|  |  |  | 2307 | Realtime disclosure of export data | [12 empty] | MoF | 0 | NA
|  |  |  | 2308 | All mining companies are transferred to LTO and have TINs | [12 empty] | MoF | 0 | NA
|  |  |  | 2309 | Disclosure of 2018 & 2019 production values, volumes and None-Tax Revenue | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan to Q1 Feb
|  |  | 2400 Output – Legal and Operational Process of Contracting and Licensing | 2401 | Analysis of Operational Process versus Practice Gaps Analysis and Map | [12 empty] | MoMP & MSG | 0 | NA | bar: Q2 May to Q2 Jun
|  |  |  | 2402 | Present findings to key Directorates and MSG - WG- 4 | [12 empty] | MoMP | 0 | NA | bar: Q3 Jul
|  |  |  | 2403 | Present findings to Higher Level Officials through a Seminar | [12 empty] | MoMP | 0 | NA | bar: Q3 Jul
|  |  |  | 2404 | Document and disclose findings in AEITI Annual Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q3 Jul
|  |  |  | 2405 | Monitor any developments or changes in practice or disclosure of information | [12 empty] | MoMP | 0 | NA | bar: Q3 Aug to Q4 Dec
|  |  | 2500 Output – Build Capacity within the MSG and the AEITI Secretariat | 2501 | Regional Workshop for Asia and Mena (MSG and AEITI Secretariat) | Q2 Jun: Depending on the actual dates | AEITI Sec | 15000 | CLDP
|  |  |  | 2502 | Seminar on BO and Significance MSG and AEITI Secretariat | Q2 Jun: Depending on the actual dates | AEITI Sec | 15000 | CLDP
|  |  |  | 2503 | Seminar on State Participation in Extractives Sector MSG and AEITI Secretariat | Q2 Jun: Depending on the actual dates | AEITI Sec | 15000 | CLDP
|  |  |  | 2504 | Regional Workshop on EITI Implementation | Q2 Jun: Depending on the actual dates | AEITI Sec | 15000 | CLDP
|  |  |  | 2505 | Presentation by AEITI on 2019 standards and its requirements (to the new MSG) | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Jun to Q4 Dec
|  |  |  | 2506 | Publication of Workshop Information on AEITI Website and Facebook etc | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Jun to Q4 Dec
|  |  |  | 2507 | Partake in Conferences/Workshops related to Transparency Initiatives in Afghanistan | [12 empty] | MSG | 0 | NA
3000 Empower Afghan citizens through capacity building and awareness and debate on the status and use of its natural resources through state oversight of exploration activities, revenues, production and export | 3100 EITI requires disclosures of information related to exploration and production, enabling stakeholders to understand the potential of the sector. | 3200 The EITI Requirements related to a transparency in exploration and production activities include: (3.1) information about exploration activities; (3.2) production data; and (3.3) export data. | 3300 Output - Assess current data collection for exploration and production, | 3301 | Gaps Analysis on “Process versus Practice” | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan
|  |  |  | 3302 | Publish exploration and production data for 2019 and 2020 | [12 empty] | MoMP | 0 | NA | bar: Q1 Feb
|  |  |  | 3303 | Identify current data collection processes, tools, standards, verification etc. | [12 empty] | MoMP | 0 | NA | bar: Q1 Mar
|  |  |  | 3304 | Develop a Draft Standard Operations Procedure (SOP) | [12 empty] | MoMP | 0 | NA | bar: Q2 Apr
|  |  |  | 3305 | Monitoring and Evaluation of Progress | [12 empty] | MSG | 0 | NA | bar: Q2 May; Q3 Aug; Q4 Nov
|  |  |  | 3306 | Feed into AEITI Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  | 3400 Output – Promote public debate and develop capacity of CSOs and stakeholders | 3401 | Maintain AEITI website space and domain | [12 empty] | AEITI Sec | 1000 | WB
|  |  |  | 3402 | Webhosting services (included new web design) for AEITI Website for 2021 | [12 empty] | AEITI Sec | 1000 | WB | bar: Q3 Sep to Q4 Oct
|  |  |  | 3403 | Social Media and Website Campaign | [12 empty] | AEITI Sec | 2000 | WB
|  |  |  | 3404 | Hiing a firm to create audio and Video AEITI messages | [12 empty] | AEITI Sec | 5000 | WB | bar: Q2 Apr to Q2 Jun
|  |  |  | 3405 | Radio Spots - to pormote public debate | [12 empty] | AEITI Sec | 3000 | WB | bar: Q3 Jul to Q4 Dec
|  |  |  | 3406 | Broadcosting TV Spots - to promote public awareness and debate | [12 empty] | AEITI Sec | 20000 | WB | bar: Q3 Aug to Q4 Dec
|  |  |  | 3407 | Create Briefing infographics For Press/Community/Officials Kits | [12 empty] | AEITI Sec | 5000 | GIZ | bar: Q2 Apr; Q4 Nov
|  |  |  | 3408 | Host Television/WebCam Journalist Debate on EI Transparency Initiatives | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Mar; Q4 Nov
|  |  |  | 3409 | Develop and Publish Communications Briefs on Legal Framework, Contracts and Licensing | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Jun to Q3 Jul
|  |  |  | 3410 | Develop Info-graphics on 6th AEITI Report (promoting public debate) | [12 empty] | AEITI Sec | 3000 | GIZ | bar: Q1 Jan
|  |  |  | 3411 | Prepare and distribute AEITI Branded Promotional Materials | [12 empty] | AEITI Sec | 10000 | WB | bar: Q1 Jan to Q1 Mar
4000 Empower Afghan citizens through capacity building and awareness and debate on the status and use of its natural resources through state oversight of Revenue Collection. | 4100 An understanding of company payments and government revenues can inform public debate about the governance of the extractive industries. The EITI requires comprehensive disclosure of company payments and government revenues from the extractive industries. " | 4200 The EITI Requirements related to revenue collection include: (4.1) comprehensive disclosure of taxes and revenues; (4.2) sale of the state’s share of production or other revenues collected in kind; (4.3) infrastructure provisions and barter arrangements; (4.4) transportation revenues; (4.5) SOE transactions; (4.6) subnational payments; (4.7) level of disaggregation; (4.8) data timeliness; and (4.9) data quality of the disclosures. | 4300 Output - Assess current data collection methodologies related to revenue collection activities (4.1-4.9) etc. for AEITI & MoMP & MoF systematic disclosure. | 4301 | Gaps Analysis on “Process versus Practice” | [12 empty] | MoMP | 0 | NA | bar: Q1 Mar
|  |  |  | 4302 | Present findings to AEITI - MSG Working Group 3- 4 | [12 empty] | MoMP | 0 | NA | bar: Q2 Apr
|  |  |  | 4303 | Develop a Draft Standard Operations Procedure (SOP) | [12 empty] | MoMP | 0 | NA | bar: Q2 Apr
|  |  |  | 4304 | Monitoring and Evaluation of Progress | [12 empty] | MSG | 0 | NA | bar: Q2 May; Q3 Aug; Q4 Nov
|  |  |  | 4305 | Feed into AEITI Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  | 4400 Output - Institutionalize Systematic Disclosure in MoMP and MoF | 4401 | Disclosure of Beneficial Ownership and Politically Exposed Persosn | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan to Q3 Sep
|  |  |  | 4402 | Disclose financial and technical criteria for award of licensese / contracing procedures | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan to Q3 Sep
|  |  |  | 4403 | Update Transparency Portal that includes key terms of all winning contracts. | [12 empty] | MoMP | 0 | NA
|  |  |  | 4404 | Systematic disclosure of SOEs financial information - prevailing rules and practices, changes to ownership, receiveables, loans and loan guarnatees, QFE, Production Data | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan
|  |  |  | 4405 | SAO to audit SOEs finanical statements to ensure data reliability | [12 empty] | SAO | 0 | NA | bar: Q2 Apr to Q3 Jul
|  |  |  | 4406 | Non tax revenues are comprehensively disclosed in easy-to-understand format | [12 empty] | MoMP | 0 | NA
|  |  |  | 4407 | Conduct training to initiate embedding - institutionalize | Q1 Jan: To be implemented in 2021
|  |  |  | 4408 | Monitoring and Evaluation of Progress | Q1 Jan: To be implemented in 2021
|  |  |  | 4409 | MSG-WG 3-4 make recommendations pre-post implementation | Q1 Jan: To be implemented in 2021
|  |  | 4500 Output – Advocate for unreleased information | 4501 | Workshop to Identify disclosure and transparency gaps | Q1 Jan: To be implemented in 2021
|  |  |  | 4502 | Link to media campaigns | Q1 Jan: To be implemented in 2021
|  |  | 4600 Output – Improve Governance and Transparency | 4601 | Develop Transparency Guidelines | Q1 Jan: To be implemented in 2021
|  |  |  | 4602 | Workshop Best Practices | Q1 Jan: To be implemented in 2021
|  |  |  | 4603 | Develop a Transparency Scorecard on State Management of Resource Revenues. See and Link: 2602 | Q1 Jan: To be implemented in 2021
|  |  |  | 4604 | Implement Transparency Scorecard | Q1 Jan: To be implemented in 2021
5000 Empower Afghan citizens through capacity building and awareness and debate on the status and use of its natural resources through state oversight of Revenue allocations. | 5100 EITI requires disclosures of information related to revenue allocations, enabling stakeholders to understand how revenues are recorded in the national and, where applicable, subnational budgets, as well as track social expenditures by companies. | 5200 The EITI Requirements related to revenue allocations include: (5.1) distribution of revenues; (5.2) subnational transfers; and (5.3) revenue management and expenditures. | 5300 Output - Assess current data collection methodologies related to revenue allocation activities (5.1-5.3) etc. for AEITI & MoMP & MoF systematic disclosure. | 5301 | Gaps Analysis on “Process versus Practice” | [12 empty] | MoF | 0 | NA | bar: Q1 Jan
|  |  |  | 5302 | Present findings to AEITI - MSG Working Group 3- 4 | [12 empty] | MoF | 0 | NA | bar: Q1 Feb
|  |  |  | 5303 | Develop a Draft Standard Operations Procedure (SOP) | [12 empty] | MoF | 0 | NA | bar: Q1 Feb
|  |  |  | 5304 | Monitoring and Evaluation of Progress | [12 empty] | MSG | 0 | NA | bar: Q1 Mar; Q3 Aug; Q4 Nov
|  |  |  | 5305 | Feed into AEITI Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  | 5400 Output – Improve Governance and Transparency | 5401 | Develop Transparency Guidelines | Q1 Jan: To be implemented in 2021
|  |  |  | 5402 | Workshop Best Practices | Q1 Jan: To be implemented in 2021
|  |  |  | 5403 | Develop a Transparency Scorecard on State Management of Resource Revenues. See and Link: 2602 | Q1 Jan: To be implemented in 2021
|  |  |  | 5404 | Implement Transparency Scorecard | Q1 Jan: To be implemented in 2021
|  |  | 5500 Output – Develop capacity through workshops, trainings, public awareness campaigns, and information sharing activities so that knowledge driven decision-making can be undertaken | 5501 | Social Media and Website Campaign | Q1 Jan: To be implemented in 2021
|  |  |  | 5502 | Radio Spots - Debates | Q1 Jan: To be implemented in 2021
|  |  |  | 5503 | Create Briefing Materials For Press/Community/Officials Kits | Q1 Jan: To be implemented in 2021
|  |  |  | 5504 | See 1800 | Q1 Jan: To be implemented in 2021
6000 Empower Afghan citizens through capacity building, awareness and debate on the status and use of its natural resources on social and environmental expenditures | 6100 The EITI encourages disclosures of information related to revenue management and expenditures, helping stakeholders to assess whether the extractive sector is leading to the desirable social and economic and environmental impacts and outcomes. | 6200 The EITI Requirements related to revenue allocations include: (6.1) social and environmental expenditures by companies; (6.2) SOE quasi‐fiscal expenditures; (6.3) an overview of the contribution of the extractive sector to the economy; and (6.4) the environmental impact of extractive activities. | 6300 Output - Assess current data collection methodologies related to social expenditure activities (6.1-6.4) etc. for AEITI & MoMP & MoF systematic disclosure. | 6301 | Gaps Analysis on “Process versus Practice” | [12 empty] | MoMP | 0 | NA | bar: Q1 Jan
|  |  |  | 6302 | Present findings to AEITI - MSG Working Group 3- 4 | [12 empty] | MoMP | 0 | NA | bar: Q1 Feb
|  |  |  | 6303 | Develop a Draft Standard Operations Procedure (SOP) | [12 empty] | MoMP | 0 | NA | bar: Q1 Feb
|  |  |  | 6304 | Monitoring and Evaluation of Progress | [12 empty] | MSG | 0 | NA | bar: Q1 Mar; Q3 Jul; Q4 Oct
|  |  |  | 6305 | Feed into AEITI Annual Progress Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  | 6400 Output – Advocate for the unreleased information and data for improved transparency | 6401 | Workshop to Identify disclosure and transparency gaps | Q1 Jan: To be implemented in 2021
|  |  |  | 6402 | Link to 6600 | Q1 Jan: To be implemented in 2021
|  |  | 6500 Output – Improve Governance and Transparency | 6501 | Develop Transparency Guidelines | Q1 Jan: To be implemented in 2021
|  |  |  | 6502 | Workshop Best Practices | Q1 Jan: To be implemented in 2021
|  |  |  | 6503 | Develop a Transparency Scorecard on State Management of Resource Revenues. See and Link: 2602 | Q1 Jan: To be implemented in 2021
|  |  |  | 6504 | Implement Transparency Scorecard | Q1 Jan: To be implemented in 2021
|  |  | 6600 Output – Capacity Building | 6601 | Social Media and Website Campaign | Q1 Jan: To be implemented in 2021
|  |  |  | 6602 | Radio Spots - Debates | Q1 Jan: To be implemented in 2021
|  |  |  | 6603 | Create Briefing Materials For Press/Community/Officials Kits | Q1 Jan: To be implemented in 2021
7000 Empower Afghan citizens through capacity building, awareness and debate on the outcomes and impacts of natural resource revenues | 7100 Regular disclosure of extractive industry data is of little practical use without public awareness, understanding of what the figures mean, and public debate about how resource revenues can be used effectively. The EITI Requirements related to outcomes and impact seek to ensure that stakeholders are engaged in dialogue about natural resource revenue management. | 7200 EITI disclosures lead to the fulfilment of the EITI Principles by contributing to wider public debate. It is also vital that lessons learnt during implementation are acted upon, that recommendations from EITI implementations are considered and acted on where appropriate and that EITI implementation is on a stable, sustainable footing. | 7300 Output- Stakeholder relations & Engagement | 7301 | Review Current Communications Streategy and Revise | [12 empty] | AEITI Sec | 0 | NA | bar: Q1 Jan
|  |  |  | 7302 | Stakeholder Identification/Mapping and Create Stakeholder Database | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Apr to Q2 May
|  |  |  | 7303 | Update Stakeholder Map and Database Bi-Annually | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 May; Q4 Oct
|  |  |  | 7304 | Workshop on Public Engagement and Consultation (MSG and Secretariat) | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Apr; Q3 Sep
|  |  |  | 7305 | Presentation of AEITI progress to Parliamentarians lower house and Upper House | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 May; Q4 Oct
|  |  | 7400 Output- Timely Communication flow with Stakeholders | 7401 | Regular-Quarterly Ministry and AEITI Communications Coordination Meetings | Q1 Jan: To be implemented in 2021
|  |  |  | 7402 | Communications and Engagement trainings CWG 2 and MoMP, MoF | Q1 Jan: To be implemented in 2021
|  |  |  | 7403 | Quarterly Meet the Press Meetings | Q1 Jan: To be implemented in 2021
|  |  |  | 7404 | Quarterly Meetings with the Press | Q1 Jan: To be implemented in 2021
|  |  | 7500 Output – To manage social media communication, public awareness and debate | 7501 | Social Media Management and public relationship | [12 empty] | AEITI Sec | 0 | NA
|  |  |  | 7502 | Quarterly Presentation to MSG on Social Media Effectiveness and Outreach | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Apr; Q3 Jul; Q4 Oct
|  |  |  | 7503 | Update and Upkeep and Monitoring of Social Media | [12 empty] | AEITI Sec | 0 | NA
|  |  |  | 7504 | Monitor media endorsements from key stakeholders based on AEITI | [12 empty] | AEITI Sec | 0 | NA
|  |  | 7600 Output- Outreach and awareness | 7601 | Workshops on Social and Environmental Expenditures; Opportunities and Benefits | [12 empty] | CSO | 8000 | GIZ | bar: Q1 Jan; Q2 May; Q3 Aug; Q4 Nov
|  |  |  | 7602 | Workshop on Community Agreements; Impacts, Benefits and Opportunities | bar: Q1 Jan; Q2 May; Q3 Aug; Q4 Nov
|  |  |  | 7603 | Workshop on Community/Stakeholder Participation Extractive Industry Revenues | bar: Q1 Jan; Q2 May; Q3 Aug; Q4 Nov
|  |  | 7700 Output – Monitoring and evaluation of extractive sector governance | 7701 | Develop Results Based Management (RBM) Performance Measurement Framework (PMF) | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Apr to Q2 May
|  |  |  | 7702 | Training Workshop on RBM- M&E for Secretariat Staff and MSG | [12 empty] | AEITI Sec | 2000 | GIZ | bar: Q2 Jun; Q3 Sep
|  |  |  | 7703 | Quarterly Focus Groups on RBM - Outcomes and Impacts | [12 empty] | AEITI Sec | 0 | NA | bar: Q3 Jul; Q4 Oct
|  |  |  | 7704 | Quarterly M&E Report to be included in the Quarterly and Final Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q2 Jun; Q3 Sep; Q4 Dec
|  |  |  | 7705 | Final RBM Report | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Nov
|  |  |  | 7706 | Presentation of Results on Results, Outcomes and Impacts of EITI Implementation | [12 empty] | AEITI Sec | 0 | NA | bar: Q4 Dec
|  |  |  | 7707 | MSG monitoring of Reform strategy and visits for verifications | [12 empty] | MSG | 5000 | WB | bar: Q1 Jan; Q2 Apr; Q3 Aug; Q4 Dec