## Summary Activity Sheet
UGANDA EITI WORK PLAN (JULY 2020 - JUNE 2022) IMPROVING THE GOVERNANCE OF EXTRACTIVE INDUSTRIES IN UGANDA FOR THE BENEFIT OF PRESENT AND FUTURE GENERATIONS. | [7 empty] | FINAL
1 | Objective 1: ENHANCE TRANSPARENCY IN THE EXTRACTIVE SECTOR so as to: Ensure transparency and accountability in the management of extractive revenues; Ensure that the legal and regulatory regime enables timely implementation of agreed projects; and manage public anxiety and expectations;"
Challenges underpinning this Objective: Limited understanding of information concerning the contracting process and disclosure of contracts under the legal and regulatory regime; need for effective disclosure of information on payments and receipts; Notion of conflicting interests between the country and extractive industry players; need for increased transparency in mining operations so as to manage public anxiety and expectations."
| Activities | EITI Standard Requirement | Outputs | Outcomes | Responsible Party | Timeline | Estimated Cost July '20 - June '21 | Estimated Cost July '21 - June '22 | Funding Source
1.1 | a) Prepare a concept paper outlining the parameters of the scoping study b) Undertake background research/ analysis on the role of private sector stakeholders (and SOEs),the status of their investments and the major challenges holding back investments |  | Background paper introducing the issues to be dicsussed in the scoping study. |  | UG EITI Sec | Jul 2020 - Sep 2020 | 23000 |  | GOU
1.2 | Research, analyse and present information for the Scoping Study on Legal framework and fiscal regime for both mining and petroleum in Uganda. | 2.1 Legal framework and fiscal regime. | Two research briefs (content for Scoping Study and EITI Report). | Improved understanding of the sector in order to strengthen the governance framework. | MSG MEMD Industry (PAU) (MOFPED) | Jul 2020 - Sep 2020 | 25250 | 0 | EU JAR
1.3 | Prepare two facts sheets on Contract and licence allocations, including explanations on commonly used technical terms, and 'procedures and practices' in contract and licence allocations for petroleum and mining. | 2.2 Contract and licence allocations. | Two fact sheets (and content for EITI Report). | Improved transparency around licence and contract awards for better scrutiny in order to hold government to account. | MSG (PAU) (MEMD) | Oct 2020 - Dec 2020 | 5000 | 5000 | EU JAR
1.4 | Scoping Study to check how far the new online mining cadastre addresses the information requirements of Register of licences and how it could interface with UG EITI website. | 2.3 Register of licences. | One (1) Gap analysis report (and content for EITI Report). | Improved transparency to ensure that mining operations are undertaken in a transparent manner. | (MEMD) | Oct 2020 - Dec 2020 | 10000 | 0
1.5 | Engage government to develop a policy and plan for contract and license disclosure and publications, documenting government's policy on disclosing extractive industry contracts and licences. | 2.4 Contracts. | Published plan for disclosing contracts and licences. | Improved transparency in licence/contract awards to ensure that the exploitation of this resource will result in lasting benefits for the public. | MSG (MEMD) Industry | Sep 2020 - Dec 2020 Jul 2021 - Sep 2021 | 5000 | 5000 | GOU
1.6 | Document the MSG's discussions and government (disclosure) policy on Beneficial ownership (covering legal provisions, actual disclosure practices and any planned reforms). | 2.5 Beneficial Ownership. | Report findings discussed in MSG and discussions published. | Improved transparency to ensure that information on ownership of firms in the extractives sector is published. | MSG Industry (MEMD) | Jul 2020 - Sep2020 Jul 2021 - Aug 2021 | 5000 | 5000 | GOU
1.7 | Undertake a Scoping Study on the reporting requirements and practices of State Owned Enterprises (SOEs) in mining and petroleum (State participation), including the prevailing rules and practice between the government and SOEs covering financing, governance, and any future changes. | 2.6 State Participation. | One research brief prepared and disseminated (and content for Scoping Study and EITI Report). | Improved understanding of the sector to ensure that UNOC is transparently and efficiently operated. | MSG (UNOC) (MEMD) (MOFPED) | July 2020 - Sep2020 | 4000 | 0
1.8 | Scoping Study (petroleum and mining) detailing the potential of the extractive sector in Exploration, Production and Exports (Including the potential to develop a policy on how the respective data will be published as the industry evolves per the standard). | 3.1 - 3.3 Exploration and production. | 2 Scoping Studies and EITI Report. | Improved transparency in order to map stakeholders and investments. | MSG (MEMD) (PAU) | Jul 2020 - Sep 2020 | 14000 | 0 | EU JAR
1.9 | Scoping Study that involves a stakeholder mapping of Artisanal and Small-Scale Mining (ASM) in order to assess their contribution to revenues, as well as their social and environmental impacts. |  | Scoping Study on ASM to inform implementation and EITI Report. | Improved transparency in ASM data, in order to ensure that ASM contribute effectively to revenue and development. | MSG (MEMD) | Jul 2020 - Sep 2020 | 10000 | 0
1.1 | Scoping Study on the gender impacts of the extractives sector and potential of EITI to improve gender equality and outcomes for women in extractives. | 6.3 Contribution of extractives to the economy. | Scoping Study on gender to inform implementation and EITI Report. | Public awareness of gender issues raised in order to ensure that they are mainstreamed into extractives governance. | MSG | Jul 2021 - Sep 2021 | 0 | 10000
1.11 | Scoping Study to track implementation of National Content policy, recommendations for EITI implementation and dissemination of findings. |  | One Report on implementation of National Content policy. | Increased participation of Ugandans in the extractives industry. | MSG PAU (MEMD) | Jan 2021 - March 2021 Jul 2021 - Sep 2021 | 10000 | 5000
1.12 | Develop a Communications Strategy (including creation of an MSG communications committee to consider National and regional launches, expanding public debate, media engagement, press releases, and talk shows). | 7.1 Public debate. | Comprehensive and fully funded Communications Strategy. | Critical mass of citizens better informed about the extractives operations in order to engage more effecively. | (CSOs) UG EITI Secretariat | Jul 2020 - Dec 2020 Jul 2021 -Dec 2021 | 30000 | 5000 | EU JAR
1.13 | Prepare, publish and disseminate the first national EITI report capturing the status and findings against all (7) EITI Requirements. |  | First EITI report covering the period decided by the MSG. | Improved transparency and accountability inorder to ensure that extractives are better managed. | UG EITI Secretariat | Jan 2022 - June 2022 |  | 120000 | EU JAR/ GOU
1.14 | Conduct outreach to various constituencies, including Parliament committees (NRC and Economy), and the media working on extractives, on findings of the Scoping studies. |  | Six awareness raising activities. | Awareness raised and capacity built to better engage MPs and media involved in extracives reporting. | MSG | Mar 2021 - June 2021 Oct 2021 - Dec 2021 | 50000 | 50000 | EU JAR
1.15 | Implement the Communications Strategy through engagement with the media, citizens and other stakeholders. |  | Media reports and coverage. | Widen awareness and understanding at national and sub-national levels. | MSG | Jan 2021 - June 2022 | 25000 | 25000 | EU JAR
1.16 | Set up, maintain and update UG-EITI website. | 7.2 Data accessibility and open data. | Functional and regularly updated website A one stop information centre for EITI in Uganda leading to increased access to information. | Improved capacity to engage from an informed position. | UG EITI Secretariat | Jul 2020 - June 2022 | 6360 | 3640 | GOU
| Sub-Total Objective 1 | [5 empty] | 222610 | 233640
2 | Objective 2: STRENGTHEN REVENUE MANAGEMENT AND ACCOUNTABILITY so as to ensure: Effective collection, optimisation and allocation of revenues; Optimal social and economic spending; and: Improved accountability in the extractives sector Ensure transparency and accountability in the management of extractive revenues.
Challenges underpinning this Objective: Increasing budget deficit; identification of priority sectors; unclear definitions of petroleum revenues; Difficulty in maximising revenue over the medium-term due to poor inter-agency coordination and low compliance; Unclear implementation of rules governing expenditure from extractive revenues; Limited knowledge of the industry
| Activities | EITI Requirement | Outputs | Outcomes | Responsible Party | Timeline | Estimated Cost (US$) July '20 - June '21 | Estimated Cost (US$) July '21 - June '22 | Funding Source
2.1 | Develop Terms of Reference for the Independent Administrator (IA); Hold meetings with OAG to discuss their potential role as IA; OAG and MSG peer learning visit to Zambia. | 4.1, 4.3, 4.5 - 4.9: Revenue collection. | Terms of Reference developed, IA identified and approved by MSG. | Improvements in extractives sector governance as a result of credible information. | MSG UG EITI Secretariat | Jul 2020 - June 2021 July 2021 - Dec 2021 | 15000 | 15000 | GOU
2.2 | Ascertain total revenues from extractives operations for the EITI Report, detailing amounts received and 'Statement of Materiality', definition of a 'project', benefit streams, mechanics of Petroleum Fund, additional benefit streams, list of Reporting Companies, and government transactions. |  | Scoping Study on Revenues Collected as preparation for first EITI Report. | Maximisation of collections from extractives; Public expectations managed; and: Improved accountability. | MSG (IA) (MOFPED) (URA) | Oct 2020 - June 2021 July 2021 - June 2022 | 69400 | 69400 | EU JAR
2.3 | Track allocations of revenues from extractives operations for EITI Report, that detail amounts allocated; including any sub-national payments (e.g. district royalties) by extractive industry companies and associated utilisation. | 5.1 - 5.3: Revenue allocations. | Revenue Allocation Report as preparation for first EITI report. | Informed engagements on benefits accruing to citizens from extractives. | MSG (MOFPED) | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100 | EU JAR
2.4 | Ascertain Social and Environmental expenditures by extractive companies (capturing 'material' social and environmental payments to communities and government, mandated and discretionary expenditures; and information on expenditures related to liabilities and remediation programmes including 'Project Affected People' (resettlement etc.); and follow-up activity to recommend possible mechanisms for regular and transparent reporting of 'Corporate and Social Responsibility' spending (CSR used when expenditures are not mandated). | 6.1 - 6.4 Social and economic spending. | Part of Scoping Report (and content for the EITI Report). | Sustainable management of extracive resources. | MSG (Industry) (NEMA) (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100
2.5 | Ascertain Quasi-fiscal expenditures by State Owned Enterprises with regard to public social expenditure, such as social services, public infrastructure, and national debt servicing etc undertaken outside of the budget. |  | Part of Scoping Report (and content for the EITI Report). | Improved management of extractive resources. | MSG (UNOC) (PAU) (MOFPED) MoWT | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100
2.6 | Analysis of Contribution of the extractives sector to the economy (e.g. size of extractive sector relative to GDP and rest of the economy, revenues, exports and employment in absolute and relative % terms); and follow up activity to develop a 'contribution tracking tools' to check whether extractive contribute as expected. | 6.3 | Part of Scoping Report (and content for the EITI Report). | Effective contribution of etractives to economic growth. | MSG (MEMD) (MOFPED) (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 10500 | 10500 | GOU
2.7 | Analysis of environmental impact of extractive activities related to social and environmental management and monitoring; and information on administrative and sanctioning processes of government, as well as environmental liabilities, rehabilitation and remediation programmes, including impacts on 'Project Affected People'. |  | Part of Scoping Report (and content for the EITI Report). | Improved awareness of impacts from extractives leading to better management and accountability of social and environmental impacts by duty bearers. | MSG (NEMA) | Oct 2020 - June 2021 July 2021 - June 2022 | 10500 | 10500
2.8 | Monitor compliance of the extractive sector with social and environmental regulations, frameworks and safeguards. Produce policy papers on areas requiring strengthening for MSG and wider stakeholder engagement. |  | 2 monitoring reports on sector compliance (petroleum and mining); and: 1 monitoring report on the pipeline. | Improved compliance with social and environmental safe guards outlined in the ESIAs. | NEMA and CSO members of MSG (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 15100 | 15100
2.9 | Engage communities on government and industry expenditures in their area, including indirect spending on 'oil roads' and other infrastructure. | 7.1 Public debate. | 8 Meetings on sub-national extractive industry revenue allocations. | Improved management of the sector. | MSG (CSOs) MoWT | Jan 2021 - June 2021 July 2021 - June 2022 | 40600 | 40600 | EU JAR
2.1 | Disseminate EITI Report findings and recommendations (including 'knowledge products' like policy briefs, position papers) |  | One(1) national and four(4) Regional dissemination meetings based on knowledge products. | Improved capacity of citizens to engage leading to better etractives governance. | MSG (CSOs) | Jan 2022 - June 2022 |  | 39100 | GOU
2.11 | Hold national meeting and high level strategic dialogue on data and improved extractives governance. |  | Two (2) strategic engagements held. | Improved compliance and governance. | MSG | Sep 2020 Oct 2020 | 31500 |  | EU JAR
| Sub-Total Objective 2 | [5 empty] | 255900 | 263500
3 | Objective 3: BUILD THE OPERATIONAL AND TECHNICAL CAPACITY OF THE MSG AND SECRETARIAT TO ENSURE EITI IS EFFECTIVELY IMPLEMENTED.
Challenges underpinning this Objective: Currently, there is a limited understanding of the extractives sector and what is involved in overseeing EITI implementation.
| Activities | EITI Requirement | Outputs | Outcomes | Responsible Party | Timeline | Estimated Cost (US$) July '20 - June '21 | Estimated Cost (US$) July '21 - June '22 | Funding Source
3.1 | Conduct induction for MSG members (including by MSG members) on key EITI implementation issues; and trainings on specific issues including the following: taxation, systematic disclosure (based on the Standard Data Template), Petroleum Fund, Fiscal Rules and Beneficial Ownership. | 1. Oversight by the MSG | One (1) Induction training and two (2) specific trainings held. | MSG members' knowledge, understanding and appreciation of the EITI standard improved. | UG EITI Sec | Jul 2020 Mar 2021 Jul 2021 | 41460 | 39000
3.2 | Hold quarterly MSG meetings for the Secretariat to report on the progress of activities and for the MSG to monitor and track overall performance in implementing EITI. |  | At least eight meetings held over the two years. | Fully active and effectively engaged MSG. | UG EITI Sec | Jul 2020 - June 2022 | 21200 | 21200 | GOU
3.3 | Undertake training, including by regional peer support for the MSG and the Independent Administrator in planning and delivering Requirement 4, designing and completing the reporting templates and preparing the first EITI Report. |  | 2 Training sessions held (including with Independent Administrator) | Secretariat staff members knowledge, understanding and appreciation of delivery issues. | UG EITI Sec | Oct 2020 Jul - Dec 2021 | 30500 | 30500
3.4 | Prepare Candidature Application and make a submission to the EITI Board. |  | Candidature Application completed. | Uganda approved as an EITI Candidate country. | UG EITI Sec | Ongoing | 0 | 0 | GOU
3.5 | Organise strategic meetings for MSG members to foster improved co-ordination and information flow. |  | Sector specific trainings held anually. | Better co-ordinated MSG linked in to constituencies. | MSG | Oct 2020 Oct 2021 | 25220 | 25220 | EU JAR
3.6 | Undertake a study to identify possible obstacles to EITI implementation and risk mitigation strategies (for 1.5 Work plan c)iii.). |  | Gap analysis report. | Smooth implementation of EITI. | UG EITI Sec | July - Sep 2020 | 12750 | 0 | EU JAR
3.7 | One (1) strategic engagement with top management of the Ministry of Finance and one (1) strategic engagement with the Ministry of Energy and Mineral Development to ensure high level buy-in and public commitment (identify and support inter-agency mechanisms for coordination and collaboration). |  | At least three (3) High level pronouncements of support and commitment to EITI made. | Increased buy-in of key government ministries . | UG EITI Sec | Aug 2020 Sep 2020 | 7400 |  | EU JAR
3.8 | Development of a Monitoring and evaluation (M&E) strategy for the Secretariat to implement and for the MSG to use in tracking implementation. |  | M&E strategy. | Improved strategic focus. | UG EITI Sec | July - Dec 2020 | 14250 | 0
3.9 | Organise field visits to the extractive regions for Secretariat and MSG members. | 7.1 Public debate | Four field visits conducted. | Increased awareness of MSG members . | UG EITI Sec | Nov 2020, Mar 2021, Nov 2021, Mar 2022 | 39200 | 39200 | EU JAR
3.1 | Study to detail status of 1) data accessibility and (2) steps being taken towards the realisation of an open data policy. | 7.2 Data accessibility and open data | Open Data Policy document. | All data produced is openly available to be used. | UG EITI Sec | Jul - Sep 2021 | 11725 | 0
3.11 | Secretariat support to the MSG - General and administration expenses. |  | Running Secretariat and MSG. | Operational efficiency in delivering EITI implementation. | MOFPED | 2020 and 2021 | 395000 | 395000 | MOFPED
| Sub-Total Objective 3 | [5 empty] | 598705 | 550120
| Grand Total MSG Work-plan | [5 empty] | 1077215 | 1047260
Note on H6: Gloria Mugambe: these are 2 deliverables hence 10k each
Note on I9: Gloria Mugambe: for publication of the disclosure plan
Note on H10: Gloria Mugambe: Policy
Note on I10: Gloria Mugambe: Implementation
Note on I17: Gloria Mugambe: includes funds for validation

## Objective One
UGANDA EITI WORK PLAN (JULY 2020 - JUNE 2022) IMPROVING THE GOVERNANCE OF EXTRACTIVE INDUSTRIES IN UGANDA FOR THE BENEFIT OF PRESENT AND FUTURE GENERATIONS. | [7 empty] | FINAL
1 | Objective 1: ENHANCE TRANSPARENCY IN THE EXTRACTIVE SECTOR so as to: Ensure transparency and accountability in the management of extractive revenues; Ensure that the legal and regulatory regime enables timely implementation of agreed projects; and manage public anxiety and expectations:"
Challenges underpinning this Objective: Limited understanding of information concerning the contracting process and disclosure of contracts under the legal and regulatory regime; need for effective disclosure of information on payments and receipts; Notion of conflicting interests between the country and extractive industry players; need for increased transparency in mining operations so as to manage public anxiety and expectations."
| Activities | EITI Standard Requirement | Outputs | Outcomes | Resp. Party | Timeline | July '20 - June '21 | July '21 - June '22 | Funding Source
1.1 | a) Prepare a concept paper outlining the parameters of the scoping study b) Undertake background research/ analysis on the role of private sector stakeholders (and SOEs), the status of their investments and the major challenges holding back investments |  | 1) Background paper introducing the issues to be dicsussed in the scoping study. 2) Study on private sector role, status and challenges. |  | UG EITI Sec | Jul 2020 - Sep 2020 | 23000 |  | GOU
1.2 | Research, analyse and present information for the Scoping Study on Legal framework and fiscal regime for both mining and petroleum in Uganda. | 2.1 Legal framework and fiscal regime. | Two research briefs on the legal framework and fiscal regime (content for Scoping Study and EITI Report). | Improved understanding of the sector in order to strengthen the governance framework. | MSG MEMD Industry (PAU) (MOFPED) | Jul 2020 - Sep 2020 | 25250 | 0 | EU JAR
1.3 | Prepare two facts sheets on Contract and licence allocations, including explanations on commonly used technical terms, and 'procedures and practices' in contract and licence allocations for petroleum and mining. | 2.2 Contract and licence allocations. | Two fact sheets (and content for EITI Report). | Improved transparency around licence and contract awards for better scrutiny in order to hold government to account. | MSG (PAU) (MEMD) | Oct 2020 - Dec 2020 | 5000 | 5000 | EU JAR
1.4 | Scoping Study to check how far the new online mining cadastre addresses the information requirements of Register of licences and how it could interface with UG EITI website. | 2.3 Register of licences. | One (1) Gap analysis report (and content for EITI Report). | Improved transparency to ensure that mining operations are undertaken in a transparent manner. | (MEMD) | Oct 2020 - Dec 2020 | 10000 | 0
1.5 | Engage government to develop a policy and plan for contract and license disclosure and publications, documenting government's policy on disclosing extractive industry contracts and licences). | 2.4 Contracts. | Published plan for disclosing contracts and licences. | Improved transparency in licence/contract awards to ensure that the exploitation of this resource will result in lasting benefits for the public. | MSG (MEMD) Industry | Sep 2020 - Dec 2020 Jul 2021 - Sep 2021 | 5000 | 5000 | GOU
1.6 | Document the MSG's discussions and government (disclosure) policy on Beneficial ownership (covering legal provisions, actual disclosure practices and any planned reforms). | 2.5 Beneficial Ownership. | Report findings discussed in MSG and discussions published. | Improved transparency to ensure that information on ownership of firms in the extractives sector is published. | MSG Industry (MEMD) | Jul 2020 - Sep 2020 Jul 2021 - Aug 2021 | 5000 | 5000 | GOU
1.7 | Undertake a Scoping Study on the reporting requirements and practices of State Owned Enterprises (SOEs) in mining and petroleum (of State participation), including the prevailing rules and practice between the government and SOEs covering financing, governance, and any future changes. | 2.6 State Participation. | One research brief prepared and disseminated (and content for Scoping Study and EITI Report) | Improved understanding of the sector to ensure that UNOC is transparently and efficiently operated. | MSG (UNOC) (MEMD) (MOFPED) | Jul 2020 - Sep 2020 | 4000 | 0
1.8 | Scoping Study (petroleum and mining) detailing the potential of the extractive sector in Exploration, Production and Exports, including the potential to develop a policy on how the respective data will be published as the industry evolves per the standard. | 3.1 - 3.3 Exploration and production. | 2 Scoping Studies and EITI Report. | Improved transparency in order to map stakeholders and investments. | MSG (MEMD) (PAU) | Jul 2020 - Sep 2020 | 14000 | 0 | EU JAR
1.9 | Scoping Study that involves a stakeholder mapping of Artisanal and Small-Scale Mining (ASM) in order to assess their contribution to revenues, as well as their social and environmental impacts. |  | Scoping Study on ASM to inform implementation and EITI Report. | Improved transparency in ASM data, in order to ensure that ASM contribute effectively to revenue and development. | MSG (MEMD) | Jul 2020 - Sep 2020 | 10000 | 0
1.1 | Scoping Study on the gender impacts of the extractives sector and potential of EITI to improve gender equality and outcomes for women in extractives. | 6.3 Contribution of extractives to the economy. | Scoping Study on gender to inform implementation and EITI Report. | Public awareness of gender issues raised in order to ensure that they are mainstreamed into extractives governance. | MSG | Jul 2021 - Sep 2021 | 10000 | 0
1.11 | Scoping Study to track implementation of National Content policy, recommendations for EITI implementation and dissemination of findings. |  | One Report on implementation of National Content policy. | Increased participation of Ugandans in the extractives industry. | MSG PAU (MEMD) | Jan 2021 - March 2021 Jul 2021 - Sep 2021 | 10000 | 5000
1.12 | Develop a Communications Strategy (including creation of an MSG communications committee to consider National and regional launches, expanding public debate, media engagement, press releases, and talk shows). | 7.1 Public debate. | Comprehensive and fully funded Communications Strategy. | Critical mass of citizens better informed about the extractives operations in order to engage more effecively. | (CSOs) UG EITI Sec | Jul 2020 - Dec 2020 Jul 2021 -Dec 2021 | 30000 | 5000 | EU JAR
1.13 | Prepare, publish and disseminate the first national EITI report capturing the status and findings against all (7) EITI Requirements. |  | First EITI report covering the period decided by the MSG. | Improved transparency and accountability inorder to ensure that extractives are better manged. | UG EITI Sec | Jan 2022 - June 2022 |  | 120000 | EU JAR/ GOU
1.14 | Conduct outreach to various constituencies, including Parliament committees (NRC and Economy), and the media working on extractives, on findings of the Scoping studies. |  | Six awareness raising activities. | Awareness raised and capacity built to better engage MPs and media involved in extracives reporting. | MSG | Mar 2021 - June 2021 Oct 2021 - Dec 2021 | 50000 | 50000 | EU JAR
1.15 | Implement the Communications Strategy through engagement with the media, citizens and other stakeholders. |  | Media reports and coverage. | Widen awareness and understanding at national and sub-national levels. | MSG | Jan 2021 - June 2022 | 25000 | 25000 | EU JAR
1.16 | Set up, maintain and update UG-EITI website. | 7.2 Data accessibility and open data | Functional and regularly updated website A one stop information centre for EITI in Uganda leading to increased access to information. | Improved capacity to engage from an informed position. | UG EITI Sec | Jul 2020 - June 2022 | 6360 | 3640 | GOU
| Sub-Total Objective 1 | [5 empty] | 232610 | 223640 | 456250
Note on H6: Gloria Mugambe: these are 2 deliverables hence 10k each
Note on I9: Gloria Mugambe: for publication of the disclosure plan
Note on H10: Gloria Mugambe: Policy
Note on I10: Gloria Mugambe: Implementation
Note on I17: Gloria Mugambe: includes funds for validation

## Objective 2
2 | Objective 2: STRENGTHEN REVENUE MANAGEMENT AND ACCOUNTABILITY so as to ensure: Effective collection, optimisation and allocation of revenues; Optimal social and economic spending; and: Improved accountability in the extractives sector; Ensure transparency and accountability in the management of extractive revenues.
Challenges underpinning this Objective: Increasing budget deficit; identification of priority sectors; unclear definitions of petroleum revenues; Difficulty in maximising revenue over the medium-term due to poor inter-agency coordination and low compliance; Unclear implementation of rules governing expenditure from extractive revenues; Limited knowledge of the industry.
| Activities | EITI Standard Requirement | Outputs | Outcomes | Resp. Party | Timeline | July '20 - June '21 | July '21 - June '22 | Funding Source
2.1 | Develop Terms of Reference for the Independent Administrator (IA); Hold meetings with OAG to discuss their potential role as IA; OAG and MSG benchmarking visit to Zambia. | 4.1, 4.3, 4.5 - 4.9: Revenue collection. | Terms of Reference developed, IA identified and approved by MSG. | Improvements in extractives sector governance as a result of credible information. | MSG UG EITI Sec | Jul 2020 - June 2021 July 2021 - Dec 2021 | 15000 | 15000 | GOU
2.2 | Ascertain total revenues from extractives operations for the EITI Report, detailing amounts received and 'Statement of Materiality', definition of a 'project', benefit streams, mechanics of Petroleum Fund, additional benefit streams, list of Reporting Companies, and government transactions. |  | Scoping Study on Revenues Collected as preparation for first EITI Report. | Maximisation of collections from extractives; Public expectations managed; and: Improved accountability. | MSG (IA) (MOFPED) (URA) | Oct 2020 - June 2021 July 2021 - June 2022 | 69400 | 69400 | EU JAR
2.3 | Track allocations of revenues from extractives operations for EITI Report, that detail amounts allocated; including any sub-national payments (e.g. district royalties) by extractive industry companies and associated utilisation. | 5.1 - 5.3: Revenue allocations. | Revenue Allocation Report as preparation for first EITI report. | Informed engagements on benefits accruing to citizens from extractives. | MSG (MOFPED) | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100 | EU JAR
2.4 | Ascertain Social and Environmental expenditures by extractive companies (capturing 'material' social and environmental payments to communities and government, mandated and discretionary expenditures; and information on expenditures related to liabilities and remediation programmes including 'Project Affected People' (resettlement etc.); and follow-up activity to recommend possible mechanisms for regular and transparent reporting of 'Corporate and Social Responsibility' spending (CSR used when expenditures are not mandated). | 6.1 - 6.4 Social and economic spending. | Part of Scoping Report (and content for the EITI Report). | Sustainable management of extractive resources. | MSG (Industry) (NEMA) (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100
2.5 | Ascertain Quasi-fiscal expenditures by State Owned Enterprises with regard to public social expenditure, such as social services, public infrastructure, and national debt servicing etc undertaken outside of the budget. |  | Part of Scoping Report (and content for the EITI Report). | Improved management of extractive resources. | MSG (UNOC) (PAU) (MOFPED) | Oct 2020 - June 2021 July 2021 - June 2022 | 21100 | 21100
2.6 | Analysis of Contribution of the extractives sector to the economy (e.g. size of extractive sector relative to GDP and rest of the economy, revenues, exports and employment in absolute and relative % terms); and follow up activity to develop a 'contribution tracking tools' to check whether extractive contribute as expected. | 6.3 The contribution of the extractive sector to the economy | Part of Scoping Report (and content for the EITI Report). | Effective contribution of extractives to economic growth. | MSG (MEMD) (MOFPED) (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 10500 | 10500 | GOU
2.7 | Analysis of environmental impact of extractive activities related to social and environmental management and monitoring; and information on administrative and sanctioning processes of government, as well as environmental liabilities, rehabilitation and remediation programmes, including impacts on 'Project Affected People'. |  | Part of Scoping Report (and content for the EITI Report). | Improved awareness of impacts from extractives leading to better management and accountability of social and environmental impacts by duty bearers. | MSG (NEMA) | Oct 2020 - June 2021 July 2021 - June 2022 | 10500 | 10500
2.8 | Monitor compliance of the extractive sector with social and environmental regulations, frameworks and safeguards. Produce policy papers on areas requiring strengthening for MSG and wider stakeholder engagement. |  | 2 monitoring reports on sector compliance (petroleum and mining); and: 1 monitoring report on the pipeline.' | Improved compliance with social and environmental safe guards outlined in the ESIAs. | NEMA and CSO members of MSG (PAU) | Oct 2020 - June 2021 July 2021 - June 2022 | 15100 | 15100
2.9 | Engage communities on government and industry expenditures in their area, including indirect spending on 'oil roads' and other infrastructure. | 7.1 Public debate | 8 Meetings on sub-national extractive industry revenue allocations. | Management of public expectations and improved accountability | MSG (CSOs) | Jan 2021 - June 2021 July 2021 - June 2022 | 40600 | 40600 | EU JAR
2.1 | Disseminate EITI Report findings and recommendations (including 'knowledge products' like policy briefs, position papers). |  | One(1) national and four(4) Regional dissemination meetings based on knowledge products. | Improved capacity of citizens to engage leading to better etractives governance. | MSG (CSOs) | Jan 2022 - June 2022 |  | 39100 | GOU
2.11 | Hold national meeting and high level strategic dialogue on data and improved extractives governance. |  | Two (2) strategic engagements held. | Improved compliance and governance. | MSG | Sep 2020 Oct 2020 | 31500 |  | EU JAR
| Sub-Total Objective 2 | [5 empty] | 255900 | 263500 | 519400

## Objective 3
3 | Objective 3: BUILD THE OPERATIONAL AND TECHNICAL CAPACITY OF THE MSG AND SECRETARIAT TO ENSURE EITI IS EFFECTIVELY IMPLEMENTED.
Challenges underpinning this Objective: Limited understanding of the extractives sector and what is involved in overseeing EITI implementation.
| Activities | EITI Standard Requirement | Outputs | Outcomes | Resp. Party | Timeline | July '20 - June '21 | July '21 - June '22 | Funding Source
3.1 | Conduct induction for MSG members (including by MSG members) on key EITI implementation issues; and trainings on specific issues selected from the following: taxation, systematic disclosure (based on the Standard Data Template), Petroleum Fund, Fiscal Rules and Beneficial Ownership. | 1. Oversight by the MSG. | One (1) Induction training and two (2) specific trainings held. | MSG members' knowledge, understanding and appreciation of the EITI standard improved. | UG EITI Sec | Jul 2020 Mar 2021 Jul 2021 | 41460 | 39000
3.2 | Hold quarterly MSG meetings for the Secretariat to report on the progress of activities and for the MSG to monitor and track overall performance in implementing EITI. |  | At least eight meetings held over the two years. | Fully active and effectively engaged MSG. | UG EITI Sec | Jul 2020 - June 2022 | 21200 | 21200 | GOU
3.3 | Undertake training, including by regional peer support for the Secretariat staff and the Independent Administrator in planning and delivering Requirement 4, designing and completing the reporting templates and preparing the first EITI Report. |  | 2 Training sessions held (including with Independent Administrator). | Secretariat staff members knowledge, understanding and appreciation of delivery issues. | UG EITI Sec | Oct 2020 Jul - Dec 2021 | 30500 | 30500
3.4 | Prepare Candidature Application and make a submission to the EITI Board. |  | Candidature Application completed. | Uganda approved as an EITI Candidate country. | UG EITI Sec | Ongoing | 0 | 0 | GOU
3.5 | Organise strategic meetings for MSG members to foster improved co-ordination and information flow. |  | Sector specific trainings held anually. | Better co-ordinated MSG linked in to constituencies. | MSG | Oct 2020 Oct 2021 | 25220 | 25220 | EU JAR
3.6 | Undertake a study to identify possible obstacles to EITI implementation and risk mitigation strategies (for 1.5 Work plan c)iii.). |  | Gap analysis report. | Smooth implementation of EITI. | UG EITI Sec | July - Sep 2020 | 12750 | 0 | EU JAR
3.7 | One (1) strategic engagement with top management of the Ministry of Finance and one (1) strategic engagement with the Ministry of Energy and Mineral Development to ensure high level buy-in and public commitment (identify and support inter-agency mechanisms for coordination and collaboration). |  | At least three (3) High level pronouncements of support and commitment to EITI made. | Increased buy-in of key government ministries. | UG EITI Sec | Aug 2020 Sep 2020 | 7400 |  | EU JAR
3.8 | Development of a Monitoring and evaluation (M&E) strategy for the Secretariat to implement and for the MSG to use in tracking implementation. |  | M&E strategy. | Improved strategic focus. | UG EITI Sec | July - Dec 2020 | 14250 | 0
3.9 | Organise field visits to the extractive regions for Secretariat and MSG members. | 7.1 Public debate | Four field visits conducted. | Increased awareness of MSG members. | UG EITI Sec | Nov 2020, Mar 2021, Nov 2021, Mar 2022 | 39200 | 39200 | EU JAR
3.1 | Study to detail status of 1) data accessibility and 2) steps being taken towards the realisation of an open data policy. | 7.2 Data accessibility and open data | Open Data Policy document. | All data produced is openly available to be used. | UG EITI Sec | Jul - Sep 2021 | 11725 | 0
3.11 | Secretariat support to the MSG - General and administration activities. |  | Running Secretariat and MSG. | Operational efficiency in delivering EITI implementation. | MOFPED | 2020 and 2021 | 395000 | 395000 | MOFPED
| Sub-Total Objective 3 | [5 empty] | 598705 | 550120 | 1148825
| Grand Total (Objectives 1 2 and 3) | [5 empty] | 1077215 | 1047260

## Detailed Budget Breakdown
UGANDA EITI MSG COSTED WORKPLAN 2020-2022 (US$)
Ref: | Item description | No. of Units | Days/Month/Quarter | QTY | Unit Cost | 2020/ 2021 | 2021/ 2022 | Total Budget | Notes
1 | OBJECTIVE 1. : ENHANCE TRANSPARENCY IN EXTRACTIVES SECTOR.
1.1 | Development of the concept paper outlining the parameters of the scoping study on the extractives sector, and a second analytical piece on the role of private sector stakeholders (and SOEs), the status of their investments and the major challenges holding back additional investment.
| Consultant hired | 2 | 30 | 1 | 100 | 6000 |  | 6000
| Dissemination | 2 | 1 | 100 | 45 | 9000 |  | 9000
| Publishing & Printing reports | 2 | 1 | 200 | 20 | 8000 |  | 8000
| Sub Total |  |  |  |  | 23000 | 0 | 23000
1.2 | Undertake scoping study on Uganda's Legal framework and fiscal regime mining and Petroleum.
| Consultant hired | 2 | 50 | 1 | 200 | 20000 |  | 20000
| Validation |  |  | 1 |  | 0 |  | 0
| Conference package | 1 | 1 | 30 | 45 | 1350 |  | 1350
| Transport Refund for Participants. | 1 | 1 | 30 | 20 | 600 |  | 600
| Communication | 1 | 1 | 1 | 300 | 300 |  | 300
| Dissemination |  |  | 1 |  | 0 |  | 0
| Printing reports | 1 | 1 | 100 | 30 | 3000 |  | 3000
| Sub Total |  |  |  |  | 25250 | 0 | 25250
1.3 | Prepare two facts sheets on Contract and licence allocations petroleum and mining.
Year 1
| Consultant hired | 2 | 20 | 1 | 125 | 5000 | 0 | 5000
| Year 2 |  |  | 1 |  | 0 | 0 | 0
| Consultant hired | 2 | 20 | 1 | 125 | 0 | 5000 | 5000
| Sub Total |  |  |  |  | 5000 | 5000 | 10000
1.4 | Study- How mining cadastre addresses info. on licences & potential of interface with UGEITI website.
| Consultant hired | 1 | 30 | 1 | 200 | 6000 |  | 6000
| Facilitator /Subject matter Specialist | 1 | 10 | 1 | 150 | 1500 |  | 1500
| Validation Workshop | 1 | 50 | 1 | 50 | 2500 |  | 2500
| Sub Total |  |  |  |  | 10000 | 0 | 10000
1.5 | Engage government to develop a plan for contract and licence disclosure and publication.
National Level
| Conference package | 4 | 20 | 1 | 45 | 3600 | 3600 | 7200
| Transport Refund for Delegates | 1 | 20 | 1 | 30 | 600 | 600 | 1200
| Communication | 1 | 1 | 1 | 350 | 350 | 350 | 700
| Facilitator /Subject matter Specialist | 4 | 1 | 1 | 50 | 200 | 200 | 400
| Assorted stationery | 1 | 1 | 1 | 250 | 250 | 250 | 500
| Sub Total |  |  |  |  | 5000 | 5000 | 10000
1.6 | Document MSG's discussion and govt Policy, Practice or proposed. reforms on Beneficial ownership disclosure.
| Facilitator /Subject matter Specialist | 2 | 1 | 1 | 100 | 200 | 200 | 400
| Strategic Engagement | 2 | 1 | 20 | 45 | 900 | 900 | 1800
| Publication of discussions and government's policy direction | 2 | 1 | 100 | 30 | 3000 | 3000 | 6000
| Media briefing | 2 | 1 | 1 | 450 | 900 | 900 | 1800
| Sub Total |  |  |  |  | 5000 | 5000 | 10000
1.7 | Study on the reporting requirements and practices of State Owned Enterprises (SOEs) in Mining and Pet.
| Consultant hired | 2 | 1 | 20 | 100 | 4000 |  | 4000
| Sub Total |  |  |  |  | 4000 | 0 | 4000
1.8 | Scoping Study detailing the potential of the extractives sector in Expl., Prod'n and Exports.
| Consultant hired | 2 | 1 | 30 | 200 | 12000 | 0 | 12000
| Validation workshop | 1 | 1 | 50 | 40 | 2000 |  | 2000
| Sub Total |  |  |  |  | 14000 |  | 14000
1.9 | Scoping Study on ASM to inform implementation and EITI Report.
| Consultant hired | 1 | 1 | 30 | 280 | 8400 |  | 8400
| validation workshop | 1 | 1 | 40 | 40 | 1600 |  | 1600
| Sub Total |  |  |  |  | 10000 | 0 | 10000
1.1 | Scoping Study - gender impacts of the extractives sector and implications for EITI outcomes.
| Consultant hired | 1 | 1 | 30 | 280 | 8400 |  | 8400
| validation workshop | 1 | 1 | 40 | 40 | 1600 |  | 1600
| Sub Total |  |  |  |  | 10000 | 0 | 10000
1.11 | Scoping Study - track implementation of National Content policy and dissemination of findings.
| Consultant hired | 1 | 30 | 1 | 150 | 4500 | 0 | 4500
| Validation workshop | 1 | 1 | 40 | 45 | 1800 | 0 | 1800
| Design, layout and printing of report | 1 | 1 | 148 | 25 | 3700 | 0 | 3700
| Dissemination of report | [5 empty] | 0 | 0
| Conference package (Venue, Meals and Refreshments) | 1 | 1 | 30 | 40 | 0 | 1200 | 1200
| Transport Facilitation | 1 | 1 | 30 | 30 | 0 | 900 | 900
| Printing of reports | 1 | 1 | 160 | 15 | 0 | 2400 | 2400
| Coordination and Mobilisation | 5 | 1 | 10 | 10 | 0 | 500 | 500
| Sub Total |  |  |  |  | 10000 | 5000 | 15000
1.12 | Develop a Communications Strategy.
| Consultant hired | 1 | 50 | 1 | 400 | 20000 | 0 | 20000
| National Launch | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conference Package | 1 | 1 | 100 | 45 | 4500 | 0 | 4500
| Transport refund - Upcountry delegates | 1 | 1 | 35 | 40 | 1400 | 0 | 1400
| Media coverage | 1 | 1 | 5 | 150 | 750 | 0 | 750
| Facilitator /Subject matter Specialist | 1 | 1 | 1 | 200 | 200 | 0 | 200
| Printing reports | 1 | 1 | 100 | 31.5 | 3150 | 0 | 3150
| TV Talkshow | 1 | 1 | 4 | 250 | 0 | 1000 | 1000
| Radio Talkshow | 1 | 1 | 4 | 200 | 0 | 800 | 800
| Newspaper supplement | 1 | 1 | 2 | 1100 | 0 | 2200 | 2200
| Media briefing | 1 | 1 | 5 | 200 | 0 | 1000 | 1000
| Sub Total |  |  |  |  | 30000 | 5000 | 35000
1.13 | Prepare, publish and disseminate the first national EITI report.
| Collection of data and drafting of first report | 1 | 60 | 1 | 1000 | 0 | 60000 | 60000
| Editing, typesetting, layout and design | 1 | 1 | 1 | 1000 | 0 | 1000 | 1000
| Printing reports | 1 | 1 | 400 | 40 | 0 | 16000 | 16000
| Dissemination | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conference package | 7 | 1 | 100 | 45 | 0 | 31500 | 31500
| Facilitator /Subject matter Specialist | 1 | 3 | 2 | 150 | 0 | 900 | 900
| Per diem/ Transport refund delegates | 1 | 2 | 42 | 50 | 0 | 4200 | 4200
| Media coverage & radio talk shows | 4 | 1 | 1 | 150 | 0 | 600 | 600
| Stationery/Communication & Mobilization | 1 | 1 | 1000 | 1 | 0 | 1000 | 1000
| Airtickets - delegates | 1 | 1 | 3 | 800 | 0 | 2400 | 2400
| Accommodation and incidentals | 3 | 1 | 3 | 180 | 0 | 1620 | 1620
| Local transportation | 3 | 1 | 1 | 100 | 0 | 300 | 300
| Sponsored newspaper article | 2 | 1 | 2 | 120 | 0 | 480 | 480
| Subtotal |  |  |  |  | 0 | 120000 | 120000
1.14 | Conduct outreach to stakeholders on findings of the Scoping studies.
| Meals and refreshment for Participants | 90 | 2 | 1 | 30 | 5400 | 5400 | 10800
| Transport for Participants - National | 60 | 1 | 1 | 40 | 2400 | 2400 | 4800
| Transport refund for Up Country Participants | 30 | 1 | 1 | 40 | 1200 | 1200 | 2400
| Perdiem for Up Country Participants | 30 | 2 | 1 | 50 | 3000 | 3000 | 6000
| Stationary-assorted Photocopying resources | 1 | 1 | 4000 | 1 | 4000 | 4000 | 8000
| Facilitator /Subject matter Specialist | 8 | 2 | 1 | 150 | 2400 | 2400 | 4800
| Printing of Scoping study reports | 4 | 1 | 200 | 35 | 28000 | 28000 | 56000
| Hire of workshop facilities/projector | 3 | 2 | 2 | 300 | 3600 | 3600 | 7200
| Sub Total |  |  |  |  | 50000 | 50000 | 100000
1.15 | Implement the Communications Strategy through engagement with the media, citizens etc.
| Venue | 4 | 1 | 2 | 300 | 2400 | 2400 | 4800
| Meals and refreshment for Participants | 60 | 1 | 2 | 20 | 2400 | 2400 | 4800
| Transport Refund for Participants.- National | 60 | 1 | 2 | 20 | 2400 | 2400 | 4800
| DSA up country ppts | 60 | 2 | 2 | 40 | 9600 | 9600 | 19200
| Transport Refund Up country Participants | 30 | 1 | 2 | 25 | 1500 | 1500 | 3000
| Hire of vehicles /Fuel | 2 | 8 | 2 | 150 | 4800 | 4800 | 9600
| Communication | 2 | 1 | 1 | 250 | 500 | 500 | 1000
| Facilitator /Subject matter Specialist | 4 | 1 | 1 | 150 | 600 | 600 | 1200
| Assorted stationery | 2 | 1 | 1 | 400 | 800 | 800 | 1600
| Sub Total |  |  |  |  | 25000 | 25000 | 50000
1.16 | Set up, maintain and update UG-EITI website.
| Design, domain name registration and hosting | 1 | 1 | 1 | 2720 | 2720 | 0 | 2720
| Maintenance, revision and content upgrade | 1 | 12 | 2 | 110 | 2640 | 2640 | 5280
| Annual subscription | 1 | 1 | 2 | 500 | 1000 | 1000 | 2000
| Sub-Total |  |  |  |  | 6360 | 3640 | 10000
| Sub-Total Objective 1 |  |  |  |  | 222610 | 223640 | 456250
2 | OBJECTIVE 2: STRENGTHEN REVENUE MANAGEMENT AND ACCOUNTABILITY
2.1 | Develop ToRs for the Independent Administrator (IA); OAG and MSG benchmarking visits.
| Consultant hired | 1 | 26 | 1 | 150 | 3900 | 3900 | 7800
| Strategic meeting to review ToRs | 1 | 1 | 20 | 45 | 900 | 900 | 1800
| Airickets | 1 | 1 | 6 | 700 | 4200 | 4200 | 8400
| Accommodation and incidentals | 1 | 4 | 6 | 150 | 3600 | 3600 | 7200
| Per diem for delegates | 1 | 4 | 6 | 100 | 2400 | 2400 | 4800
| Subtotal |  |  |  |  | 15000 | 15000 | 30000
2.2 | Ascertain total revenues from extractives operations for the EITI Report.
| Consultant hired- petroleum | 1 | 30 | 2 | 500 | 30000 | 30000 | 60000
| Consultant hired- mining | 1 | 30 | 2 | 500 | 30000 | 30000 | 60000
| Strategic meeting to review reports- conference package | 2 | 50 | 2 | 45 | 9000 | 9000 | 18000
| Facilitator /Subject matter Specialist | 1 | 1 | 2 | 200 | 400 | 400 | 800
| Sub Total |  |  |  |  | 69400 | 69400 | 138800
2.3 | Track allocations of revenues from extractives operations for EITI Report.
| Consultant hired- petroleum | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Consultant hired- mining | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Strategic meeting to review reports- conference package | 1 | 30 | 2 | 45 | 2700 | 2700 | 5400
| Facilitator /Subject matter Specialist | 1 | 1 | 2 | 200 | 400 | 400 | 800
| Sub Total |  |  |  |  | 21100 | 21100 | 42200
2.4 | Ascertain Social and Environmental expenditures by extractive companies.
| Consultant hired- petroleum | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Consultant hired- mining | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Strategic meeting to review reports- conference package | 1 | 30 | 2 | 45 | 2700 | 2700 | 5400
| Facilitator /Subject matter Specialist | 1 | 1 | 2 | 200 | 400 | 400 | 800
| Sub Total |  |  |  |  | 21100 | 21100 | 42200
2.5 | Ascertain Quasi-fiscal expenditures by State Owned Enterprises with regard to public social expenditure.
| Consultant hired- petroleum | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Consultant hired- mining | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Strategic meeting to review reports- conference package | 1 | 30 | 2 | 45 | 2700 | 2700 | 5400
| Facilitator /Subject matter Specialist | 1 | 1 | 2 | 200 | 400 | 400 | 800
| Sub Total |  |  |  |  | 21100 | 21100 | 42200
2.6 | Analysis of Contribution of the extractives sector to the economy.
| Consultant hired | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Experts meeting to review and validate the study- conference package | 1 | 1 | 20 | 45 | 900 | 900 | 1800
| Transport refund for experts panel | 1 | 1 | 20 | 30 | 600 | 600 | 1200
| Sub Total |  |  |  |  | 10500 | 10500 | 21000
2.7 | Analysis of Social & environmental impact of extractive activities.
| Consultant hired | 1 | 30 | 1 | 300 | 9000 | 9000 | 18000
| Experts meeting to review and validate the study- conference package | 1 | 1 | 20 | 45 | 900 | 900 | 1800
| Transport refund for experts panel | 1 | 1 | 20 | 30 | 600 | 600 | 1200
| Sub Total |  |  |  |  | 10500 | 10500 | 21000
2.8 | Monitor compliance of the extractive sector with social and environmental regulations, frameworks and safeguards & produce policy briefs.
| Consultant Fees | 1 | 30 | 1 | 250 | 7500 | 7500 | 15000
| Designing and printing monitoring reports | 1 | 1 | 90 | 40 | 3600 | 3600 | 7200
| Validation |  |  | 1 |  | 0 | 0 | 0
| Venue | 1 | 1 | 1 | 300 | 300 | 300 | 600
| Meals and refreshment for Participants | 1 | 1 | 40 | 25 | 1000 | 1000 | 2000
| Transport Refund for Participants. | 1 | 1 | 40 | 30 | 1200 | 1200 | 2400
| Transport for MSG Members | 1 | 1 | 20 | 60 | 1200 | 1200 | 2400
| Communication | 1 | 1 | 1 | 300 | 300 | 300 | 600
| Sub-Total |  |  |  |  | 15100 | 15100 | 30200
2.9 | Engage communities on government and industry expenditures in their area, including indirect spending on 'oil roads' and other infrastructure.
| Facilitator /Subject matter Specialist | 4 | 1 | 1 | 150 | 600 | 600 | 1200
| Per Diem for Up country Participants (30 ppts) | 4 | 1 | 30 | 40 | 4800 | 4800 | 9600
| Transport for Up Country Participants at Regional Level | 4 | 1 | 30 | 25 | 3000 | 3000 | 6000
| Refreshments/ meals | 4 | 1 | 30 | 25 | 3000 | 3000 | 6000
| Venue Hire & Projector & PAS | 4 | 1 | 1 | 250 | 1000 | 1000 | 2000
| Vehicle hire for organization and coordination | 4 | 4 | 4 | 150 | 9600 | 9600 | 19200
| Accommodation and incidentals for MSG team | 4 | 3 | 13 | 100 | 15600 | 15600 | 31200
| Communication & Media coverage | 1 | 1 | 1 | 2250 | 2250 | 2250 | 4500
| Stationery - Assorted | 50 | 1 | 1 | 15 | 750 | 750 | 1500
| Sub Total |  |  |  |  | 40600 | 40600 | 81200
2.1 | Disseminate EITI Report findings and recommendations (including 'knowledge products' like policy briefs, position papers).
National Level
| Facilitator /Subject matter Specialist | 2 | 1 | 1 | 200 | 0 | 400 | 400
| Conference package | 1 | 1 | 40 | 45 | 0 | 1800 | 1800
| Transport refund | 1 | 1 | 40 | 30 | 0 | 1200 | 1200
| Stationery | 80 | 1 | 1 | 15 | 0 | 1200 | 1200
| Moblisation & communication | 1 | 1 | 1 | 4500 | 0 | 4500 | 4500
| Media coverage | 1 | 1 | 4 | 350 |  | 1400 | 1400
| Printing policy briefs, position papers | 4 | 1 | 50 | 35 |  | 7000 | 7000
| Subnational level | [5 empty] | 0 | 0
| Facilitator /Subject matter Specialist | 4 | 1 | 1 | 200 | 0 | 800 | 800
| Conference package | 4 | 1 | 25 | 40 | 0 | 4000 | 4000
| Transport refund | 4 | 1 | 25 | 30 | 0 | 3000 | 3000
| Stationery | 60 | 1 | 1 | 15 | 0 | 900 | 900
| Moblisation & communication | 1 | 1 | 1 | 4500 | 0 | 4500 | 4500
| Media coverage | 1 | 1 | 4 | 350 |  | 1400 | 1400
| Printing policy briefs, position papers | 4 | 1 | 50 | 35 |  | 7000 | 7000
| Sub Total |  |  |  |  | 0 | 39100 | 39100
2.11 | Hold national meeting and high level strategic dialogue on data and improved extractives governance.
| Facilitator /Subject matter Specialist | 6 | 1 | 1 | 500 | 3000 |  | 3000
| Accommodation for facilitators | 4 | 5 | 1 | 200 | 4000 |  | 4000
| Meals and incidentals for experts | 4 | 5 | 1 | 20 | 400 |  | 400
| Conference package | 2 | 1 | 70 | 45 | 6300 | 0 | 6300
| Transport Refund for Participants. | 2 | 1 | 70 | 40 | 5600 | 0 | 5600
| DSA up country ppts | 2 | 1 | 20 | 40 | 1600 | 0 | 1600
| Coordinatin and mobilization | 2 | 1 | 1 | 1000 | 2000 | 0 | 2000
| Media coverage | 4 | 1 | 4 | 350 | 5600 | 0 | 5600
| Printing and stationery for conference - briefs, bulletins | 2 | 1 | 100 | 15 | 3000 | 0 | 3000
| Sub Total |  |  |  |  | 31500 | 0 | 31500
| Sub-Total Objective 2 |  |  |  |  | 255900 | 263500 | 519400
3 | OBJECTIVE 3: BUILD THE OPERATIONAL AND TECHNICAL CAPACITY OF THE MSG AND SECRETARIAT
3.1 | Conduct induction and specialized trainings for MSG members.
Induction
| Facilitator /Subject matter Specialist | 1 | 1 | 3 | 500 | 1500 | 0 | 1500
| Airticket facilitator | 1 | 1 | 1 | 1400 | 1400 |  | 1400
| Ground transport and incidentals facilitators | 1 | 4 | 3 | 30 | 360 |  | 360
| Conference package | 1 | 3 | 30 | 50 | 4500 | 0 | 4500
| Accommodation | 1 | 3 | 30 | 200 | 18000 | 0 | 18000
| Communication & coordination | 1 | 1 | 1 | 800 | 800 | 0 | 800
| Stationary-assorted | 10 | 1 | 1 | 30 | 300 | 0 | 300
| Transport refund for Participants | 1 | 1 | 30 | 50 | 1500 | 0 | 1500
| Per diem for participants | 1 | 4 | 30 | 100 | 12000 | 0 | 12000
Specalized training
| Facilitator | 4 | 2 | 2 | 300 | 0 | 4800 | 4800
| Conference Package | 2 | 2 | 30 | 50 | 0 | 6000 | 6000
| Accommodation | 2 | 2 | 30 | 150 | 0 | 18000 | 18000
| Transport refund | 1 | 1 | 30 | 40 | 0 | 1200 | 1200
| Per diem | 1 | 3 | 30 | 100 | 0 | 9000 | 9000
| Communication & coordination | 1 | 1 | 1 | 800 | 800 | 0 | 800
| Printing/ Stationary-assorted | 10 | 1 | 1 | 30 | 300 | 0 | 300
| Sub Total |  |  |  |  | 41460 | 39000 | 80460
3.2 | Hold quarterly MSG meetings.
| Conference package | 8 | 1 | 30 | 45 | 10800 | 10800 | 21600
| Facilitator | 8 | 1 | 1 | 100 | 800 | 800 | 1600
| Transport refund | 8 | 1 | 30 | 50 | 4000 | 4000 | 8000
| Coordination and organization | 8 | 1 | 1 | 400 | 3200 | 3200 | 6400
| Stationery /Printing | 8 | 1 | 1 | 300 | 2400 | 2400 | 4800
| Sub Total |  |  |  |  | 21200 | 21200 | 42400
3.3 | Undertake training, including by regional peer support for the Secretariat staff and the Independent Administrator.
| Facilitator/expert- airticket | 2 | 1 | 1 | 1000 | 2000 | 2000 | 4000
| Accommodation for experts | 2 | 4 | 1 | 150 | 1200 | 1200 | 2400
| Conference package | 2 | 2 | 20 | 45 | 3600 | 3600 | 7200
| Accommodation for participtants | 2 | 3 | 20 | 150 | 18000 | 18000 | 36000
| Transport refund | 1 | 1 | 20 | 40 | 800 | 800 | 1600
| Per diem | 1 | 2 | 20 | 50 | 2000 | 2000 | 4000
| Stationery-assorted Photocopying resources | 30 | 2 | 1 | 15 | 900 | 900 | 1800
| Organization and coordination | 1 | 1 | 1 | 2000 | 2000 | 2000 | 4000
| Sub Total |  |  |  |  | 30500 | 30500 | 61000
3.5 | Organise strategic meetings for MSG members to foster improved co-ordination and information flow.
| Conference package (Venue, Meals and Refreshments) | 2 | 1 | 47 | 45 | 4230 | 4230 | 8460
| Per Diem for Up country Participants (25 ppts) | 2 | 1 | 25 | 45 | 2250 | 2250 | 4500
| Transport for Up Country Participants at Regional Level | 2 | 1 | 25 | 40 | 2000 | 2000 | 4000
| Facilitators for the strategic engagements | 2 | 1 | 1 | 200 | 400 | 400 | 800
| Transport refund for MSG | 2 | 1 | 22 | 50 | 2200 | 2200 | 4400
| Communication and coordination | 2 | 1 | 1 | 250 | 500 | 500 | 1000
| Per diem for MSG | 4 | 1 | 22 | 50 | 4400 | 4400 | 8800
| Accommodation for MSG for strategic meetings | 2 | 3 | 22 | 70 | 9240 | 9240 | 18480
| Sub Total |  |  |  |  | 25220 | 25220 | 50440
3.6 | Undertake a study to identify possible obstacles to EITI implementation and risk mitigation strategies.
| Consultant hired | 1 | 30 | 1 | 200 | 6000 | 0 | 6000
| Validation for study ( conference package) | 1 | 1 | 30 | 50 | 1500 | 0 | 1500
| Layout, typesetting and Printing of reports | 1 | 1 | 100 | 40 | 4000 | 0 | 4000
| Transport refund for participants | 1 | 1 | 30 | 30 | 900 | 0 | 900
| Coordination and communication for organization | 1 | 1 | 1 | 350 | 350 | 0 | 350
| Sub Total |  |  |  |  | 12750 | 0 | 12750
3.7 | Strategic engagement with Ministry of Finance and Ministry of Energy and Mineral Development.
| Conference package | 2 | 1 | 30 | 50 | 3000 | 0 | 3000
| Communication and coordination | 2 | 1 | 1 | 300 | 600 | 0 | 600
| Printing and stationery - briefs, bulletins | 2 | 1 | 50 | 20 | 2000 | 0 | 2000
| Transport refund | 2 | 1 | 30 | 30 | 1800 | 0 | 1800
| Sub-Total |  |  |  |  | 7400 | 0 | 7400
3.8 | Development of a Monitoring and evaluation (M&E) strategy for the Secretariat.
| Consultant hired | 1 | 30 | 1 | 250 | 7500 | 0 | 7500
| Validation |  |  |  |  | 0 | 0 | 0
| Conference Package | 1 | 1 | 50 | 45 | 2250 | 0 | 2250
| Type setting, layout, printing and publishing | 1 | 1 | 100 | 35 | 3500 | 0 | 3500
| Communication and coordination | 1 | 1 | 1 | 400 | 400 | 0 | 400
| Reviewer of the study | 1 | 1 | 1 | 600 | 600 | 0 | 600
| Sub Total |  |  |  |  | 14250 | 0 | 14250
3.9 | Organise field visits to the extractive regions for Secretariat and MSG members.
| Transport for field visits | 2 | 5 | 1 | 200 | 2000 | 2000 | 4000
| Accommodation | 2 | 3 | 30 | 80 | 14400 | 14400 | 28800
| Meals and incidentals for MSG | 2 | 3 | 30 | 20 | 3600 | 3600 | 7200
| Communication | 2 | 1 | 1 | 400 | 800 | 800 | 1600
| Assorted stationary | 2 | 1 | 1 | 200 | 400 | 400 | 800
| Venue Hire & Projector & PAS | 2 | 4 | 1 | 200 | 1600 | 1600 | 3200
| Meals and refreshments for Participants | 2 | 2 | 25 | 20 | 2000 | 2000 | 4000
| Perdiem | 2 | 3 | 30 | 80 | 14400 | 14400 | 28800
| Sub Total |  |  |  |  | 39200 | 39200 | 78400
3.1 | Study to detail status of 1) data accessibility and (2) steps being taken towards the realisation of an open data policy.
| Consultant hired | 1 | 30 | 1 | 250 | 7500 |  | 7500
| Reviewer of the study | 1 | 1 | 1 | 600 | 600 |  | 600
| Coordination and communication for organization of validation workshop | 1 | 1 | 1 | 350 | 350 |  | 350
| Conference package to organize validation | 1 | 1 | 45 | 45 | 2025 |  | 2025
| Printing draft reports for validation | 1 | 1 | 50 | 25 | 1250 |  | 1250
| Sub Total |  |  |  |  | 11725 | 0 | 11725
3.11 | Secretariat support to the MSG - General and administration activities.
Capital Items
Personal costs
Adminstrative costs
| Sub Total |  |  |  |  | 395000 | 395000 | 790000
| Sub-Total Objective 3 |  |  |  |  | 598705 | 550120 | 1148825
| Grand total MSG Workplan |  |  |  |  | 1077215 | 1037260 | 2124475
Note on B48: Gloria: We could either have a validation or get a reviewer to review the work

## summary totals
SUMMARY TOTALS
| Year 1 | Year 2 | Total
Obj 1 | 232610 | 223640 | 456250
Obj 2 | 255900 | 263500 | 519400
Obj 3 | 598705 | 550120 | 1148825
USD: | 1087215 | 1037260 | 2124475
UGX: | 4131417000 | 3941588000 | 8073005000